## Slide 1: Project Status – 6E0022 Sculi
Product
Maturity
Integration
Maturity
Timing
Quality
Costs
Project Status
Project | 6E0022
Customers | PME / ITM LBH, LHB, LFR, LMB, LWN, LWT External users
Supported ECUs | Diesel Engines: DC4, DC5, UPCR, Lidec 1 Machines: UEC3, Master 4
Future ECUs | Diesel Engines: Lidec 2 (March 2013) Machines: Master 5 (2015)
Current version | 1.348
Volume | 2’500 users
Target Price | 200 € / license per year
Project Budget | 1.1 Mio € / year
Product Owner | P. Terreaux | AC3
Scrum Master | L. Lantier | AC3
SW Architect | F. Salvalai | AC3
SW Engineer | F. Bressoud | AC3
 | Y. Brulhart | AC3
 | O. Monney | AC3
 | P. Pombeiro | AC3
 | N. Thal | AC3
Tester | H. Turhal | AC3
Documentation | M. Catillaz | KD

## Slide 2: Project Status – 6E0022 Sculi
Scope
One diagnostic Tool for Liebherr Machines and Diesel Engines
CTQ’s
Intuitive: not an engineer tool
Performance: connection establishment time oscilloscope sampling rate quick access to functions
Stability: no freeze no need of task manager
Risks
Sculi 1 is developed in Delphi
  Bad architecture
  Maintenance on Windows 7 !
  Hard to find qualified persons with Delphi know-how !
Sculi 2 (light) must be ready for March 2013
Changes
Sculi 2 will be developed with Microsoft .Net/C#

## Slide 3: Project Status – 6E0022 Sculi
 | Major open issues | Who | Due Date | Status
1. | DPF Dashboard | Team | 01.05.2012 | 
2. | DPF Functions | Team | 01.06.2012 | 
3. | SCR Dashboard | Team | 15.05.2012 | 
4. | SCR Functions | Team | 01.06.2012 | 
5. | Integration of PAMS Licenses files | Team | 01.07.2012 | 
 | Decision need | Who | Due Date | Status
1. | Development of Sculi 2 focused on Lidec 2 | ITM + AC | 23.05.2012 | 
2. | Usage of Sontheim libraries for the development of Sculi 2 | P. Terreaux | 01.06.2012 | 
3. | Improvement of Business Model | AC |  | 
planned
overdue
done
Color Code:

## Slide 4: Project Status – 6E0022 Sculi
2012 |  |  |  |  |  |  |  |  |  | 2013 |  |  |  | 
03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05
Reserved
Sculi 2.0 RC
Scope Definition of Sculi 2.0
cw22
Sculi 2.0 Released
Stage 4 D-Sample Engines
Stage 4 B-Sample Engines
Sculi 2.0 Beta
Sculi 2.0 Alpha 1
Sculi 2.0 Alpha 2
Sculi 2.0 Alpha 3
Information Screen
cw36
Read Messages
Read Variables
Oscilloscope
Integration of PAMS Security
cw40
cw44
cw49
cw03

## Slide 5: Project Status – 6E0022 Sculi
2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Development Sculi 2.0
For basis LIDEC2 diagnostic
Sculi 2.0
Sculi 2.4
Sculi 2.8
Sculi 2.12
Development Sculi 2.4
With full LIDEC 2 diagnostic
Development Sculi 2.8
Replacing all Sculi 1
Stage 4 Engines SOP
Stage 4 D-Sample Engines
Stage 4 B-Sample Engines
Q1/2013
Q1/2014
Q1/2015
Development Sculi 2.12
With Master 5 diagnostic
Q4/2015
Diagnostic of FPT Engine D824?