## Slide 1: Project Status – Sculi (ITM)
Product
Maturity
Integration
Maturity
Timing
Quality
Costs
Project Status
Project: 6E0022
Customers: PME/ITM LFR, LMB, LHB, LWN, LWT, LBH External users
ECUs: Supported: DC4, DC5, UPCR, Lidec 1, UEC3, Master 4 Futur: Lidec 2 & Master 5
Volume: 2’500 users
Project Team
Product Owner: P. Terreaux AC3
Scrum Master: L. Lantier AC3
Soft. Architect.: F. Salvalai AC3
Soft. Engineer: F. Bressoud AC3
Soft. Engineer: Y. Brulhart AC3
Soft. Engineer: O. Monney AC3
Soft. Engineer: P. Pombeiro AC3
Soft. Engineer: N. Thal AC3
Tester: H. Turhal AC3

## Slide 2: Project Status – Sculi (ITM)
Scope
Diagnostic Tool for Liebherr Machines and Engines
CTQ’s
Performance: connection establishment time
Stability: ctrl+alt+del is forbidden
Intuitive: not an engineer tool
Risks
Sculi 1 is developed in Delphi
  Maintenance on Windows 7 is hard
  Hard to find qualified persons with Delphi know-how
Sculi 2 (light) must be ready for march 2013
Changes
Sculi 2 for Lidec 2

## Slide 3: Project Status – Sculi (ITM)
 | Major open issues | Who | Due Date | Status
1. | Define exact brake pressure via vehicle test @ LWE | Scharpf | cw17, 2012 | planned
2. | Commitment from PPT needed to meet max. temp of 100°C for engine coolant. | Gerber | cw19, 2012 | planned
3. | Chase K&S to freeze B-sample design. No 3d models received yet. | Thomas | cw18, 2012 | overdue
4. | Define Turbo Charger for D934 (end cw18) to freeze interface for flap. | Auffret | cw18, 2012 | overdue
5. | Close commercial discussion on prototype / series pricing / NRE costs with PPT | Bacza | cw19, 2012 | planned
 | Decision need | Who | Due Date | Status
1. | Escalate resource problem @ K&S. Milestones for LMB projects are all overdue. | Schindler | cw19, 2012 | planned
2. | How to proceed with 90mm flap since turbo of D934 is not defined (interface is not fix). | Petutschnig | cw19, 2012 | planned
3. | Volume split for B-samples to be decided. | Glauser | cw19, 2012 | planned
planned
overdue
done
Color Code:

## Slide 4: Project Status – Sculi (ITM)
2012 |  |  |  |  |  |  |  |  |  | 2013 |  |  |  | 
03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05
C-samples
PPT or K&S ?
C-sample Validation
@ Supplier
@ LMB
SOP
Field Tests
Preparation
D-samples
Tier 4f Motors
Design Freeze
C-samples Motor
cw19
B-samples (110mm / D9x6)
PPT
K&S / Sonceboz
cw30
Design Freeze
B-sample PPT
cw19
cw48
cw15
PPAP
cw17
B-sample Validation
@ Supplier
@ LMB
cw44
Design Freeze
B-sample K&S
cw19
B-samples (90mm / D9508)
PPT
K&S / Sonceboz
B-samples (90mm / D9x4)
PPT
cw20
Commercial discussion done
cw42
FTG LH80 (D946)
cw44
FTG L576 (D944)
cw36
FTG ZG1362 (D944)
cw37
Series Sourcing completed