## Slide 1: Lidec 2 – Sculi

## Slide 2: Agenda
Lidec 2 Milestones
Lidec 2 – Sculi: User Requirements
Definition of “Risk”
Sculi 1 or Sculi 2
Planning 2012  2015

## Slide 3: Stufe 4 Engine & Lidec 2 Milestones
Stufe 4 Motoren Planung
B-Muster Prototyp-Motoren (ohne AGN) 03/2012
C-Muster Prototype-Motoren (LMB internal only) 06/2012
D-Muster Prototyp-Motoren 01/2013
D-Muster-Motoren inkl. SCR-Anlage 02/2013
SCRF Serien Lösung (nur für 1 Motor/Leistung/Gerät*) 01/2015
Einführung Emissionstufe T4f 01/2014
LIDEC2 Planung
B3-Muster 04/2012
C-Muster 10/2012
D-Muster 04/2013
SOP 09/2013

## Slide 4: Lidec 2 – Sculi : User requirements
Markus Burri (LMB) has been defined as Key Person for the motor diagnostic
  Responsible to define what is necessary for the motor diagnostic
  Responsible for the definition of the features priorities
The general features and priorities for the Lidec 2 for March 2013 have been defined (Lidec2_user_priorities.xlsx)
  Read general information of the ECU
  Read messages (active / passive with additional info’s)
  Read variables (read only)
  Record variables over the time (oscilloscope)
A prototype has been created (Expression Blend) in order to show how the tool will looks like with the various requested features waited for this first package. This prototype has been shown and approved by Markus Burri.
An “User Requirement” document is currently written and will define the scope and functionalities of each features. This document will required the signature of the customer services for approval.

## Slide 5: Definition of “Risk”
“Risk is any potential situation or event that could negatively affect a project’s ability” (Classification and Analysis of Risks in Software Engineering - Hooman Hoodat & Hassan Rashidi)
Risk categories
  Software Requirement Risks (Lack of report for requirements, impossible requirements, …)
  Software Cost Risks (Lack of good estimation in project, technology, personal change, …)
  Software Scheduling Risks (Lack of enough skills, shortage of personnel, …)
  Software Quality Risks (Lack of testing, lack of good guidelines, …)
  Software Business Risks (Product that no one want them, …)
As Project Manager, my role is to evaluate the risk and to suggest the best way to reach the goal

## Slide 6: How to reach the goal
2 possibilities:
  Sculi 1: Add features for the support of Lidec 2 diagnostic
  Sculi 2: Starting the development of a new product
1
2

## Slide 7: Sculi 1 – Add features for the support of Lidec 2 diagnostic
What are the major risks:
  Software Cost Risks
    The bridge between Delphi and .Net/C# is not an easy job. A lot of time will be wasted and used for non-planed tasks.
    It known that the current architecture of Sculi 1 is bad (approved in LWN on 21th September 2011). Adding new features implies a large risk of regressions, when shared part of code must be changed.
  Software Scheduling Risks
    Only 2 persons are able to work on the Delphi part of Sculi 1.
    In the case we are late in the planning, it will be very hard to find qualified persons quickly with Delphi know-how.
  Software Quality Risks
    The current stability problem of Sculi 1 will be also the same for the diagnostic of Lidec 2 (bad user experience)
Advantages
  Usage of the current features available in Sculi 1
  One product for all ECUs
1

## Slide 8: Sculi 2 – Starting the development of a new product
What are the major risks:
  Software Cost Risks
    Lack of good estimation (time) in project
  Software Quality Risks
    Until all the features of Sculi 1 are migrated to Sculi 2, the usage of two diagnostic tools will be necessary
Advantages
  The user experience can be improved and focus on what the users are really waiting for
  100 % .Net/C#  better stability by using the .Net Framework (Windows XP / Windows 7 / Windows 8)
  All the Team is able to work in .Net/C# environment (knowledge)
  The integration of external libraries will be easier
  Future oriented
2

## Slide 9: Planning Sculi 2 - Lidec 2
2012 |  |  |  |  |  |  |  |  |  | 2013 |  |  |  | 
03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 04 | 05
Reserved
Sculi 2.0 RC
Scope Definition of Sculi 2.0
cw22
Sculi 2.0 Released
Stage 4 D-Sample Engines
Stage 4 B-Sample Engines
Sculi 2.0 Beta
Sculi 2.0 Alpha 1
Sculi 2.0 Alpha 2
Sculi 2.0 Alpha 3
Information Screen
cw36
Read Messages
Read Variables
Oscilloscope
Integration of PAMS Security
cw40
cw44
cw49
cw03

## Slide 10: Planning Sculi 2
2012 |  |  |  | 2013 |  |  |  | 2014 |  |  |  | 2015 |  |  | 
Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Development Sculi 2.0
For basis LIDEC2 diagnostic
Sculi 2.0
Sculi 2.4
Sculi 2.8
Sculi 2.12
Development Sculi 2.4
With full LIDEC 2 diagnostic
Development Sculi 2.8
Replacement of all Sculi 1 (Included all Machine and Engine features)
Stage 4 Engines SOP
Stage 4 D-Sample Engines
Stage 4 B-Sample Engines
Q1/2013
Q1/2014
Q1/2015
Development Sculi 2.12
With Master 5 support, workflows and pattern recognition system
Q4/2015